## Sheet1
ROPOLine | Task Order | Condom Adjusted Task Order | Country | RO Number | PO DO IO Number | Order Number | Prime Line Number | Status Name | TLP Indicator | Order Type | Fulfillment Method | Transportation Mode | Item Tracer Category | Product Category | Product ID | Product_Name | UOM | Base Unit | Base Unit Multiplier | Framework Contract | D365 Health Element | D365 Funding Source | D365 Funding Source Detail | Fiscal_Year_Funding | Estimated Lead Time in Days | Vendor Incoterm | Destination Incoterm | Illustrative Price | Ordered Quantity | Shipped Quantity | OTD OTIF Exclusion Flag | In Full (IFD) | On Time (OTD) | Between -14 and 14 | Between -30 and 30 | OTIF Categories | OTIF Between -14 and 14 | OTIF Between -30 and 30 | Average Days Late Binned | Average Days Late | Number of Shipments | Delivery Progress | Line Delivery Status | Agreed Delivery Date | Agreed Delivery Date Year | Agreed Delivery Date Year Month | Agreed Delivery Date Fiscal Year | Agreed Delivery Date Fiscal Quarter Year | Revised Agreed Delivery Date | Revised Agreed Delivery Date Year | Revised Agreed Delivery Date Year Month | Revised Agreed Delivery Date Fiscal Year | Revised Agreed Delivery Date Fiscal Quarter Year | Order Entry Date | Order Entry Date Year | Order Entry Date Year Month | Order Entry Date Fiscal Year | Order Entry Date Fiscal Quarter Year | Requested Delivery Date | Requested Delivery Date Year | Requested Delivery Date Year Month | Requested Delivery Date Fiscal Year | Requested Delivery Date Fiscal Quarter Year | Estimated Delivery Date | Estimated Delivery Date Year | Estimated Delivery Date Year Month | Estimated Delivery Date Fiscal Year | Estimated Delivery Date Fiscal Quarter Year | Latest Actual Delivery Date | Latest Actual Delivery Date Year | Latest Actual Delivery Date Year Month | Latest Actual Delivery Date Fiscal Year | Latest Actual Delivery Date Fiscal Quarter Year | RO Clarified Date | RO Sent Plan Fulfillment Date | RO Sent Sourcing RFX Event Date | Initial PSM Source Approval Date | Recipient Approval Date | USAID Approval Date | PO Released For Fulfillment Date | PO Released For Fulfillment Date Year | PO Released For Fulfillment Date Year Month | PO Released For Fulfillment Date Fiscal Year | PO Released For Fulfillment Date Fiscal Quarter Year | Committed Goods Available Date | Actual Goods Available Date | Actual Cargo Ready Date | QA Complete Date | Max Pick Up Date | Max Ship Date | Max Departure Date | Max Arrival Date | Order Cycle Time | RO Validation | Sourcing and Planning | USAID Approval | Process PO/DO | Manufacture | Pick Up | Deliver | Quality Assurance | Reason Code | Reason Code Duration
RO10021223PO100019151 | TO1 | TO1 | Mozambique | RO10021223 | PO10001915 | PO10001915 | 1 | Shipment Delivered | DCP | Purchase Order | Direct Drop | Land | Laboratory | Laboratory Consumables | 101514XUZ0AZ | Centrifuge Tube 50 mL, Polypropylene, Conical Bottom, Flat Screw Cap, Sterile, 500 Each | UNT | Each | 500 |  | HIV/AIDS | Mission Commodity Funding | PEPFAR-COP-USAID |  |  | DDP |  | 25.75 | 15 | 15 |  | Y | N | N | Y | Not On Time In Full | Not On Time In Full | On Time In Full | Between 8 and 30 | 30 | 1 | 2 | Delivered - Late | Monday, February 20, 2017 | 2017 | 2017-02 | 2017 | 2017-Q2 | Saturday, December 31, 2016 | 2016 | 2016-12 | 2017 | 2017-Q1 | Tuesday, November 1, 2016 | 2016 | 2016-11 | 2017 | 2017-Q1 | Tuesday, January 31, 2017 | 2017 | 2017-01 | 2017 | 2017-Q2 | Monday, February 20, 2017 | 2017 | 2017-02 | 2017 | 2017 Q2 | Monday, January 30, 2017 | 2017 | 2017-01 | 2017 | 2017-Q2 |  |  |  | Monday, February 20, 2017 | Monday, February 20, 2017 | Tuesday, February 21, 2017 | Thursday, June 1, 2017 | 2017 | 2017-06 | 2017 | 2017-Q3 | Monday, February 20, 2017 |  |  |  |  | Thursday, August 3, 2017 |  |  | 91 |  |  | 1 | 100
RO10060249PO100087742 | TO1 | TO1 | Zambia | RO10060249 | PO10008774 | PO10008774 | 2 | Shipment Delivered | DCP | Purchase Order | Direct Drop | Land | Laboratory | Laboratory Reagents | 101203XUZ0B9 | ABX Minotrol 16 Twin-Pack, High, 2 x 2.5 mL, 1 Pack | PKG | Pack | 1 | Non-Framework | HIV/AIDS | Mission Commodity Funding | PEPFAR-COP-USAID | FY19 | 140 | DDP | DDP | 137 | 210 | 210 |  | Y | Y | Y | Y | On Time In Full | On Time In Full | On Time In Full |  | 4 | 1 | 2 | Delivered - On Time | Monday, December 16, 2019 | 2019 | 2019-12 | 2020 | 2020-Q1 | Monday, December 16, 2019 | 2019 | 2019-12 | 2020 | 2020-Q1 | Tuesday, August 7, 2018 | 2018 | 2018-08 | 2018 | 2018-Q4 | Monday, December 16, 2019 | 2019 | 2019-12 | 2020 | 2020-Q1 | Monday, December 16, 2019 | 2019 | 2019-12 | 2020 | 2020 Q1 | Friday, December 20, 2019 | 2019 | 2019-12 | 2020 | 2020-Q1 |  |  |  | Thursday, August 23, 2018 | Thursday, August 23, 2018 | Thursday, August 23, 2018 | Friday, September 21, 2018 | 2018 | 2018-09 | 2018 | 2018-Q4 | Monday, December 16, 2019 |  |  |  |  | Thursday, December 26, 2019 |  |  | 501 |  |  | 0 | 29
RO10071106PO1001100012 | TO1 | TO1 | Zambia | RO10071106 | PO10011000 | PO10011000 | 12 | Shipment Delivered | DCP | Purchase Order | Direct Drop | Land | Laboratory | Laboratory Reagents | 101203XUZ0B9 | ABX Minotrol 16 Twin-Pack, High, 2 x 2.5 mL, 1 Pack | PKG | Pack | 1 | Non-Framework | HIV/AIDS | Mission Commodity Funding | PEPFAR-COP-USAID | FY19 | 147 | DDP | DDP | 137 | 26 | 26 |  | Y | N | N | Y | Not On Time In Full | Not On Time In Full | On Time In Full | Between 8 and 30 | 18 | 1 | 2 | Delivered - Late | Sunday, December 1, 2019 | 2019 | 2019-12 | 2020 | 2020-Q1 | Sunday, December 1, 2019 | 2019 | 2019-12 | 2020 | 2020-Q1 | Tuesday, February 19, 2019 | 2019 | 2019-02 | 2019 | 2019-Q2 | Sunday, December 1, 2019 | 2019 | 2019-12 | 2020 | 2020-Q1 | Tuesday, December 31, 2019 | 2019 | 2019-12 | 2020 | 2020 Q1 | Thursday, December 19, 2019 | 2019 | 2019-12 | 2020 | 2020-Q1 |  |  |  | Tuesday, March 5, 2019 | Tuesday, March 5, 2019 | Wednesday, March 6, 2019 | Tuesday, March 19, 2019 | 2019 | 2019-03 | 2019 | 2019-Q2 | Sunday, December 1, 2019 |  |  |  |  | Thursday, January 2, 2020 |  |  | 304 |  |  | 1 | 13
RO10039248PO100059151 | TO1 | TO1 | Zambia | RO10039248 | PO10005915 | PO10005915 | 1 | Shipment Delivered | DCP | Purchase Order | Direct Drop | Land | Laboratory | Laboratory Reagents | 101357XUZ04K | HumaLyte Plus Daily Cleaning Solution, 100 mL | BOT | mL | 100 | Non-Framework | HIV/AIDS | Mission Commodity Funding | PEPFAR-COP-USAID | FY18 | 105 | DDP | DDP | 64.4 | 12 | 12 |  | Y | Y | Y | Y | On Time In Full | On Time In Full | On Time In Full |  | 3 | 1 | 2 | Delivered - On Time | Saturday, March 31, 2018 | 2018 | 2018-03 | 2018 | 2018-Q2 | Saturday, March 31, 2018 | 2018 | 2018-03 | 2018 | 2018-Q2 | Friday, September 22, 2017 | 2017 | 2017-09 | 2017 | 2017-Q4 | Saturday, March 31, 2018 | 2018 | 2018-03 | 2018 | 2018-Q2 | Friday, April 6, 2018 | 2018 | 2018-04 | 2018 | 2018 Q3 | Tuesday, April 3, 2018 | 2018 | 2018-04 | 2018 | 2018-Q3 |  |  |  | Thursday, November 16, 2017 | Thursday, November 16, 2017 | Tuesday, November 21, 2017 | Tuesday, April 3, 2018 | 2018 | 2018-04 | 2018 | 2018-Q3 | Saturday, March 31, 2018 |  |  |  |  | Tuesday, April 3, 2018 |  |  | 194 |  |  | 5 | 133
RO10036286PO100045152 | TO1 | TO1 | Mozambique | RO10036286 | PO10004515 | PO10004515 | 2 | Shipment Delivered | DCP | Purchase Order | Direct Drop | Land | Laboratory | Laboratory Equipment | 101158XUZ01S | m2000 Halogen Lamp, Replacement [09K33-01], 1 Each | UNT | Each | 1 | Non-Framework | HIV/AIDS | Mission Commodity Funding | PEPFAR-COP-USAID |  |  | DDP | DDP | 150 | 48 | 48 |  | Y | Y | Y | Y | On Time In Full | On Time In Full | On Time In Full |  | -7 | 1 | 2 | Delivered - On Time | Wednesday, December 27, 2017 | 2017 | 2017-12 | 2018 | 2018-Q1 | Thursday, November 30, 2017 | 2017 | 2017-11 | 2018 | 2018-Q1 | Wednesday, August 9, 2017 | 2017 | 2017-08 | 2017 | 2017-Q4 | Wednesday, December 27, 2017 | 2017 | 2017-12 | 2018 | 2018-Q1 | Wednesday, December 27, 2017 | 2017 | 2017-12 | 2018 | 2018 Q1 | Thursday, November 23, 2017 | 2017 | 2017-11 | 2018 | 2018-Q1 |  |  |  | Monday, August 28, 2017 | Tuesday, August 29, 2017 | Tuesday, August 29, 2017 | Monday, October 2, 2017 | 2017 | 2017-10 | 2018 | 2018-Q1 | Wednesday, December 27, 2017 |  |  |  |  | Thursday, November 23, 2017 |  |  | 107 |  |  | 0 | 34
RO10040230PO100048206 | TO1 | TO1 | Mozambique | RO10040230 | PO10004820 | PO10004820 | 6 | Shipment Delivered | DCP | Purchase Order | Direct Drop | Land | Laboratory | Laboratory Consumables | 100352XUZ0B9 | COBAS TaqMan AmpliPrep, Flapless Sample Processing Unit, 12 Racks of 24, 1 Pack | PKG | Pack | 1 | Framework | HIV/AIDS | Mission Commodity Funding | PEPFAR-COP-USAID | FY18 | 154 | DDP | DDP | 260 | 306 | 306 |  | Y | Y | Y | Y | On Time In Full | On Time In Full | On Time In Full |  | -6 | 1 | 2 | Delivered - On Time | Wednesday, March 14, 2018 | 2018 | 2018-03 | 2018 | 2018-Q2 | Wednesday, March 14, 2018 | 2018 | 2018-03 | 2018 | 2018-Q2 | Monday, October 9, 2017 | 2017 | 2017-10 | 2018 | 2018-Q1 | Wednesday, February 28, 2018 | 2018 | 2018-02 | 2018 | 2018-Q2 | Saturday, March 3, 2018 | 2018 | 2018-03 | 2018 | 2018 Q2 | Thursday, March 8, 2018 | 2018 | 2018-03 | 2018 | 2018-Q2 |  |  |  | Tuesday, October 10, 2017 | Tuesday, October 10, 2017 | Wednesday, October 11, 2017 | Friday, February 16, 2018 | 2018 | 2018-02 | 2018 | 2018-Q2 | Saturday, March 3, 2018 |  |  |  |  | Thursday, March 8, 2018 |  |  | 151 |  |  | 1 | 128
RO10042143PO100057024 | TO1 | TO1 | Uganda | RO10042143 | PO10005702 | PO10005702 | 4 | Shipment Delivered | DCP | Purchase Order | Direct Drop | Land | Laboratory | Laboratory Consumables | 100352XUZ0B9 | COBAS TaqMan AmpliPrep, Flapless Sample Processing Unit, 12 Racks of 24, 1 Pack | PKG | Pack | 1 | Non-Framework | HIV/AIDS | Mission Commodity Funding | PEPFAR-COP-USAID | FY18 | 70 | DDP | DDP | 260 | 150 | 150 |  | Y | Y | Y | Y | On Time In Full | On Time In Full | On Time In Full |  | 5 | 1 | 2 | Delivered - On Time | Thursday, March 15, 2018 | 2018 | 2018-03 | 2018 | 2018-Q2 | Thursday, March 15, 2018 | 2018 | 2018-03 | 2018 | 2018-Q2 | Thursday, October 19, 2017 | 2017 | 2017-10 | 2018 | 2018-Q1 | Thursday, March 15, 2018 | 2018 | 2018-03 | 2018 | 2018-Q2 | Thursday, March 15, 2018 | 2018 | 2018-03 | 2018 | 2018 Q2 | Tuesday, March 20, 2018 | 2018 | 2018-03 | 2018 | 2018-Q2 |  |  |  | Wednesday, November 15, 2017 | Wednesday, November 15, 2017 | Friday, December 1, 2017 | Thursday, February 15, 2018 | 2018 | 2018-02 | 2018 | 2018-Q2 | Thursday, March 15, 2018 |  |  |  |  | Thursday, March 22, 2018 |  |  | 153 |  |  | 16 | 76
RO10033104PO100046904 | TO1 | TO1 | Mozambique | RO10033104 | PO10004690 | PO10004690 | 4 | Shipment Delivered | DCP | Purchase Order | Direct Drop | Land | Laboratory | Laboratory Consumables | 100352XUZ0B9 | COBAS TaqMan AmpliPrep, Flapless Sample Processing Unit, 12 Racks of 24, 1 Pack | PKG | Pack | 1 | Non-Framework | HIV/AIDS | Mission Commodity Funding | PEPFAR-COP-USAID |  | 0 | DDP |  | 260 | 65 | 65 |  | Y | Y | Y | Y | On Time In Full | On Time In Full | On Time In Full |  | -4 | 1 | 2 | Delivered - On Time | Friday, December 22, 2017 | 2017 | 2017-12 | 2018 | 2018-Q1 | Friday, December 22, 2017 | 2017 | 2017-12 | 2018 | 2018-Q1 | Monday, June 5, 2017 | 2017 | 2017-06 | 2017 | 2017-Q3 | Friday, December 22, 2017 | 2017 | 2017-12 | 2018 | 2018-Q1 | Friday, December 22, 2017 | 2017 | 2017-12 | 2018 | 2018 Q1 | Monday, December 18, 2017 | 2017 | 2017-12 | 2018 | 2018-Q1 |  |  |  | Monday, July 31, 2017 | Monday, July 31, 2017 | Monday, July 31, 2017 | Tuesday, October 3, 2017 | 2017 | 2017-10 | 2018 | 2018-Q1 | Friday, December 29, 2017 |  |  |  |  | Monday, December 18, 2017 |  |  | 197 |  |  | 0 | 64
RO10060249PO100087747 | TO1 | TO1 | Zambia | RO10060249 | PO10008774 | PO10008774 | 7 | Shipment Delivered | DCP | Purchase Order | Direct Drop | Land | Laboratory | Laboratory Reagents | 101202XUZ0B9 | ABX Minotrol 16 Twin-Pack, Normal, 2 x 2.5 mL, 1 Pack | PKG | Pack | 1 | Non-Framework | HIV/AIDS | Mission Commodity Funding | PEPFAR-COP-USAID | FY19 | 140 | DDP | DDP | 137 | 210 | 210 |  | Y | Y | Y | Y | On Time In Full | On Time In Full | On Time In Full |  | 4 | 1 | 2 | Delivered - On Time | Monday, December 16, 2019 | 2019 | 2019-12 | 2020 | 2020-Q1 | Monday, December 16, 2019 | 2019 | 2019-12 | 2020 | 2020-Q1 | Tuesday, August 7, 2018 | 2018 | 2018-08 | 2018 | 2018-Q4 | Monday, December 16, 2019 | 2019 | 2019-12 | 2020 | 2020-Q1 | Monday, December 16, 2019 | 2019 | 2019-12 | 2020 | 2020 Q1 | Friday, December 20, 2019 | 2019 | 2019-12 | 2020 | 2020-Q1 |  |  |  | Thursday, August 23, 2018 | Thursday, August 23, 2018 | Thursday, August 23, 2018 | Friday, September 21, 2018 | 2018 | 2018-09 | 2018 | 2018-Q4 | Monday, December 16, 2019 |  |  |  |  | Thursday, December 26, 2019 |  |  | 501 |  |  | 0 | 29